Contents

1. Overview of Microsoft Project 2010

Success Factors to Project Management

What is a Project?

Project Management Software

Why use Microsoft Project 2010?

Formulate a Strategy

Success Checklist

Exploring the Ribbon

What is the Ribbon?

Task Tab

Resource Tab

Project Tab

View Tab

Format Tab

File Tab (Backstage) Task Tab

Exploring the Project 2010 Views

What is a View?

Task Views

Resource Views

Combining Views

1. Initializing a Project

Creating and Configuring Calendars

How Calendars Work in Project 2010?

Creating a Base Calendar

Setting Working Hours and Days

Setting Non-Working Hours and Days

Setting Calendar Options

Saving the Base Calendar to the Global Template

Practice: Creating Calendars

Configuring Schedule/Display Options

Understanding Duration vs. Work/Effort

What is Effort Driven Scheduling? Understanding Task Types

Setting Schedule Options

Setting Display and General Options

Practice: Configuring Schedule/Display Options

Creating and Saving a Project Schedule

Creating a New Project Schedule

Adding Project Information

Creating a Schedule from an Excel Workbook

Crating a Schedule from a SharePoint Task List

Importance of Naming Standards

Saving the Schedule

Setting Read-Only and Password Attributes

Save and Send Options

Practice: Creating and Saving a Project Schedule

1. Creating a Work Breakdown Structure

Overview of WBS

What is WBS?

Task Categories

Best Practices

Creating the Work Breakdown Structure

Entering Tasks

Working with Task Information

Outlining Tasks into a Hierarchy

Displaying Outline Numbers & WBS

Customizing WBS Codes

Practice: Creating a Work Breakdown Structure

Estimating Task Lengths

Overview of Estimating

Entering Estimates

Practice: Entering Estimates

Entering Milestones

How to Set a Milestone

Apply Milestone Filters

Best Practices

Practice: Entering Milestones

1. Creating Task Relationships

Automatic vs. Manual Scheduling

Scheduling Overview

Manual vs. Automatic Scheduling

When to Use Manual Scheduling

Setting Scheduling Option

Adjusting Tasks in Manual Mode

Practice: Working with Manual and Automatic Scheduling

Working with Dependencies

Task Dependency Types

Creating Dependencies Viewing Dependencies

Best Practices for Using Dependencies

Practice: Working with Dependencies

Understanding Leads and Lags

What is Lead Time?

What is Lag Time?

Best Practices

Practice: Working with Leads and Lags

1. Configuring Advanced Task Information

Working with Task Constraints

What are Constraints?

Constraint Types

Actions that Create Automatic Constraints

Effects of Constraints

Practice: Working with Task Constraints

Advanced Task Management

Task Deadlines

Using the Task Inspector

Using Task Form Views

Adding Notes to Tasks

Applying a Calendar to a Task Splitting Tasks

Changing the Start Date of a Project

Working with Timescale

Practice: Working with Advanced Task Management

1. Creating Resources

Resource Types Work

Resources Cost

Resources Material

Resources Budget

Resources

Creating Work and Material Resources

Creating a Work Resource

Resource Information – General

Resource Information – Costs

Resource Information – Notes and Custom Fields

Inserting Resources

Creating a Material Resource

Practice: Creating Work and Material Resources

Creating Cost and Budget Resources

Overview of Costing in Microsoft Project

Creating a Cost Resource

Creating a Budget Resource

Entering a Fixed Cost

Practice: Creating Cost and Budget Resources

Assigning Material, Cost and Budget Resources

Assign a Cost Resource

Assign a Material Resource

Assign a Budget Resource

Practice: Working with Resources

1. Assigning and Leveling Work Resources

Overview of Assignments

What is an Assignment?

Assignment Formula

How to Create Assignments

Creating Fixed Unit Assignments

Creating Fixed Work Tasks

Practice: Creating Assignments

Factors that Affect Assignments

Percentage Assignments

Assignment Units and Peak Units Values

Resource Calendar

Delaying an Assignment

Assigning Resources with Variable Units

Rules for Creating Assignments

Best Practices

Practice: Working with Factors that Affect Assignments

Viewing Resource Assignments

Resource Usage View

Task Usage View

Team Planner View

Practice: Viewing Resource Assignments

Resolving Resource Overallocations

Understanding Overallocations

Views to Identify Overallocations

Leveling Resources – Project Manager

Leveling Resources – Microsoft Project

Practice: Resolving Resource Overallocations

1. Reviewing and Finalizing the Schedule

Working with Groups and Filters

What are Groups?

How to Use Groups

What are Filters?

How to Use Filters

How to Use Highlights

How to Use AutoFilter

Practice: Working with Groups and Filters

Understanding the Critical Path Method

What is a Critical Path?

Formatting Views to Display Critical Path

Setting Slack Tolerance

Shortening the Critical Path

Practice: Working with the Critical Path

Setting a Project Baseline

What is a Baseline?

Fields Used in Setting a Baseline

Setting the Baseline

Updating a Baseline

Views Using Baseline Data

Practice: Setting a Project Baseline

Appendix

Appendix – Default Groups

Appendix – Default Filters

1. Tracking and Updating Projects

Overview of Tracking Projects

What is Tracking

Tracking Methods

Options that Affect Tracking

Best Practice of Tracking

Tracking Projects

Preparing a Task to be Tracked

Using Percent Complete

Using Task Level Tracking – Task Duration

Using Task Level Tracking – Task Work

Using Resource Level Tracking – Task Details

Using Resource Level Tracking – Resource Usage

Practice: Working with Tracking Methods

Updating Milestones, Material and Cost Resources

Updating Milestones

Updating Material Resources

Updating Cost Resources

Practice: Updating Milestones, Material and Cost Resources

Updating Project Status

Overview of Tracking Cycle

Setting a Status Date

Rescheduling Incomplete Work

Getting the Project Back on Track

Practice: Updating Project Status

1. Managing Multiple Projects and Resource Pools

Linking Multiple Projects

Overview of Multiple Projects

Cross-Linking Projects

Analyzing the Effects of Changing Values

Practice: Linking Multiple Projects

Working with Master and Sub-Projects

Overview of Master Projects

Creating a Master Project and Inserting Sub-Projects

Leveling Resources Across Projects

Practice: Working with Master and Sub-Projects

Working with Resource Pools

What is a Resource Pool?

Creating a Resource Pool

How to Share Resources across Multiple Projects

Viewing Resource Usage in the Resource Pool

Practice: Working with Resource Pools

1. Customizing Project 2010 Features

Customizing the User Interface

Customize Quick Access Toolbar

Customizing the Ribbon

Exporting / Importing the Customization File

Customizing Formats and Styles

Overview on Custom Formats and Styles

Customizing Gantt Views

Customizing Timeline Views

Working with the Organizer

What is an Object & Available Objects

Define Setting in Organizer

Using the Organizer to Share Objects

Creating Custom Objects

Creating a Custom Field

Creating a Custom Filter

Creating a Custom Group

Creating a Custom Table

Creating a Custom View

1. Communicating Project Information

Defining Print Settings

Print Settings

Define Page Setup

Working with Copy Picture to Office Wizard

Working with Project Reports

Selecting Project Reports

Editing Project Report

Creating Custom Project Reports

Working with Visual Reports

Overview of Visual Reports

Anatomy of a Pivot Table

Viewing Visual Report

Creating Visual Report Templates

Collaborating Project Information

Export Project Table to Excel

Publish a Project to SharePoint List

Import a SharePoint List into Project